## Slide 1
Secure M-Band components before the EMS signs.
Future Electronics offer: place orders in Sword’s name now, transfer to EMS at no cost.
0€ cost. 1 decision.
Apr 20, 2026 · André Faria · For Jorge Garcia

## Slide 2
The Situation — Lead Times Confirmed Today
Manuel Beito (Future Electronics) · Apr 20, 2026
Component | Supplier | Lead Time | Status
AS7058A | AMS-OSRAM | 30 weeks | PO overdue since Apr 5
BMI270 | Bosch | 12 weeks | Pre-alloc required Q4
NPM1300 | Nordic Semiconductor | 16 weeks | Available
DA14531 | Renesas | 14 weeks | Jul 1 price increase
Battery (Grepow) | Grepow | 16–18 wk sea / 12 wk air | MP path confirmed
SGM41106A | SGMicro | 14 weeks | Samples ETA this week
Source: OI 345b4a7d–81c3

## Slide 3
The Collision — Critical Path at Risk
AS7058A — 30 weeks
PO needed today → stock arrives Nov 14 at earliest
BMI270 — Q4 pre-allocation window closing
Bosch requires commitment before EMS is selected
Macronix — Q2 allocation risk
Flagged Mar 12. Not yet covered.
Without action, the EMS inherits a broken critical path.

## Slide 4
The Opportunity — Zero-Cost Window
What we gain
• Component priority secured now
• No-cost transfer to EMS when selected
• Zero lead-time loss on critical parts
• Price lock before Renesas Jul 1 increase
What we risk by waiting
• EMS restarts LT clock from zero
• Re-qualification of sources adds weeks
• Renesas price increase hits Jul 1
• BMI270 pre-alloc window missed → Q1 risk
Place in Sword’s name now. Move to EMS at no cost. Zero-cost window.

## Slide 5
The Ask — One Decision
Approve placing PO for AS7058A today + pre-allocation requests for BMI270 and Grepow (sea-ship) this week?
Approve
Jorge Garcia
Execute
André Faria · TPM alignment: Miguel Pais
Timeline
Today
André opens PO with Future Electronics
+48h
Confirmation back to Jorge
+1 week
Pre-alloc requests sent (BMI270 + Grepow)
Source: OI 345b4a7d–81c3 · Future Electronics offer confirmed Apr 20, 2026